| MONTH | COMPREHENSIVE COMMUNITY INITIATIVES (CCI) INVENTORY | FEDERAL COLLABORATION PROJECT (FCP) | DELINQUENCY DEVELOPMENT STATEMENT (DDS) |
| --- | --- | --- | --- |
| DECEMBER 2007 | 12/14: Draft Work Plan Completed Outline of Lit Review 12/21: Work Plan Comments Rec’d 12/28: Final Work Plan Completed Lit Review Outline Approved | 12/14: Draft Work Plan Completed Outline of Lit Review 12/21: Work Plan Comments Rec’d 12/28: Final Work Plan Completed Lit Review Outline Approved | 12/14: Draft Work Plan Completed 12/21: Work Plan Comments Rec’d 12/28: Final Work Plan Completed |
| JANUARY 2008 | 1/18: Background Materials Completed 1/25: Inventory List Completed |  |  |
| FEBRUARY 2008 | 2/1: Proposal Memo/Protocol Completed | 2/29: Proposal Memo/Protocol Completed |  |
| MARCH 2008 | 3/7: Draft Lit Review Completed/ Distributed for Review 3/21: Draft Lit Review Comments Due | 3/7: Draft Lit Review Completed/ Distributed for Review 3/21: Draft Lit Review Comments Due |  |
| APRIL 2008 | 4/4: Final Lit Review Completed 4/18: Completion of Site Visits and Other Discussions 4/25: Analysis of Findings Completed | 4/4: Final Lit Review Completed 4/28: Completion of Site Visits and Other Discussions | 4/1: Prelim. Draft Completed 4/4: Draft Distributed to Agencies for Comment |
| MAY 2008 | 5/2: Draft Inventory Due Interim Briefing with Fed Staff 5/16: Inv. Meeting Planning Call Inventory Comments Due 5/23: Inv. Meeting Work Plan Completed 5/30: Final Inventory Completed |  | 5/1: Draft Comments Due 5/22: Final Draft Completed |
| JUNE 2008 | 6/6: Inv. Meeting Agenda and Panelist /Presenter /Participant ID Completed 6/20: Travel Arrangements Completed | 6/6: Analysis of Findings Completed | 6/6: Edited Final Draft Presented to Council for Approval 6/20: Final Report Produced/Posted |
| JULY 2008 | 7/18: Invitational Meeting (approximate) |  |  |
| AUGUST 2008 | 8/1: Post Meeting Services Completed 8/15: Guidebook Outline Completed 8/29: Guidebook Outline Comments and Revisions from Staff Due and Forwarded to Designees | 8/15: Guidebook Outline Completed 8/29: Guidebook Outline Comments and Revisions from Staff Due and Forwarded to Designees |  |
| SEPTEMBER 2008 | 9/12: Outline Presented for Formal Approval 9/26: Draft Guidebook/Web Design Completed | 9/12: Outline Presented for Formal Approval 9/26: Draft Guidebook Completed |  |
| OCTOBER 2008 | 10/17: Comments Due from Agencies on Guidebook/Web Design | 10/17: Comments Due from Agencies on Guidebook |  |
| NOVEMBER 2008 | 11/7: Final Guidebook Completed Beta Version of Web Version Opened for Testing by Staff/Designees | 11/7: Final Guidebook Completed Beta Version of Web Version Opened for Testing by Staff/Designees |  |
| DECEMBER 2008 | 12/5: Guidebook Web Tools Presented for Council Approval 12/19: Web Tools Launched | 12/5: Guidebook Web Tools Presented for Council Approval 12/19: Web Tools Launched |  |